## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
RSI | My wrists could be aching | Ensure I move wrists about | To keep my wrists safe for the future | Very Unlikely | Minor | Low
Losing my Work | Loss of work will affect the entire Project and Will lead to regression in progress. | Ensure I continuously save my work and ensure it is present. | to keep all work securely saved in multiple places by pushing work regularly after completion. | Very Unlikely | Catastrophic | High
Injury | Involvement in activity could lead to injury during project and become incapable of finishing project | Ensure i exercise responsibly and rest well. | be cautious when exercising to prevent injury and eat a balanced diet to decrease recovery time if injured. | Moderate | Major | Medium
Computer Malfunctioning | If Computer malfunctions it will mean I can’t use It any more to do the project. | ensure i check my computer health regularly | monitor computer health and reduce the usage of CPU intensive applications. | Very Unlikely | Hazardous | Medium
GitHub Servers being down | I would then be unable to access the remote work to enhance development | Ensure my I regularly check GitHub status. | ensure my remote repository is up-to date with my GitHub repository at all times. | Very Unlikely | Catastrophic | Medium
Mentor is not present | Mentor not available for support due to illness Or being occupied with others from the cohort | be patient until he is avaible to help me and do other work and come back to that particular task | use resources on QA Community | Moderate | Minor | Low Medium
Bad Internet / No Internet | Loss of internet preventing access to GitHub And not being able to reach my cohort on Teams | Ensure i have a strong internet Provider. | ensure that the Wi-Fi is strong and use my phone hotspot if internet goes down. | Unlikely | Hazardous | Medium
Problems in Merging between two branches | Could happen due to incorrect branching workflow Which will lead to merge conflicts during feature merging. | Ensure i know what branch i am working on and the changes i've made to it. | keep track of the feature-branch workflow and ensure to branch off develop branch to follow branching best practises and that the branches have a shared history. | Moderate | Minor | Low Medium